## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies
Project Initiation | John Smith | 2024-01-01 | 2024-01-07 | Completed | 7
Requirements Gathering | Jane Doe | 2024-01-08 | 2024-01-25 | In Progress | 18 | Project Initiation
Design Phase | Alex Chen | 2024-01-26 | 2024-02-15 | Not Started | 20 | Requirements Gathering
Development | Team A | 2024-02-16 | 2024-03-31 | Not Started | 46 | Design Phase
Testing & QA | Lisa Park | 2024-04-01 | 2024-04-15 | Not Started | 15 | Development
Deployment | IT Team | 2024-04-16 | 2024-04-18 | Not Started | 3 | Testing & QA
Post-Deployment Review | Project Manager | 2024-04-19 | 2024-04-20 | Not Started | 2 | Deployment