## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Resource Allocation | Priority
Project Kickoff Meeting | John Smith | 2024-03-01 | 2024-03-01 | Completed | None | Project Manager, HR | High
Requirement Gathering Workshop | Sarah Lee | 2024-03-04 | 2024-03-10 | In Progress | Project Kickoff Meeting | Business Analysts, Stakeholders | High
Design Phase - Wireframes & UI | Michael Chen | 2024-03-11 | 2024-03-25 | Not Started | Requirement Gathering Workshop | UX Team, Design Lead | Medium
Development Phase - Backend Setup | David Kim | 2024-03-26 | 2024-04-15 | Not Started | Design Phase - Wireframes & UI | Dev Team, Backend Lead | High
Development Phase - Frontend Implementation | Linda Park | 2024-04-16 | 2024-05-10 | Not Started | Backend Setup Complete | Frontend Team, QA Lead | High
Testing & Quality Assurance | Robert Taylor | 2024-05-11 | 2024-05-30 | Not Started | Frontend Implementation | QA Team, Test Manager | High
User Acceptance Testing (UAT) | Elena Rodriguez | 2024-06-03 | 2024-06-15 | Not Started | Testing & QA Complete | Stakeholders, End Users | High
Deployment & Go-Live | John Smith | 2024-06-16 | 2024-06-16 | Not Started | UAT Completion | DevOps, IT Operations | Critical