## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days)
Project Initiation | Jane Doe | 2024-03-01 | 2024-03-07 | Completed | 7
Scope Definition | John Smith | 2024-03-08 | 2024-03-15 | In Progress | 8
Resource Allocation | Lisa Chen | 2024-03-16 | 2024-03-22 | Not Started | 7
Risk Assessment | Michael Brown | 2024-03-23 | 2024-03-30 | Not Started | 8
Workflow Design | Sarah Lee | 2024-04-01 | 2024-04-10 | Not Started | 10
Implementation Phase | Team Lead | 2024-04-11 | 2024-05-15 | Not Started | 35
Review & Optimization | Jane Doe | 2024-05-16 | 2024-05-31 | Not Started | 16