## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Priority
Project Kickoff Meeting | Jane Doe | 2024-03-01 | 2024-03-01 | Completed | 100% | None | High
Requirement Gathering | John Smith | 2024-03-02 | 2024-03-15 | In Progress | 65% | Kickoff Meeting | High
Design Phase | Lisa Chen | 2024-03-16 | 2024-04-10 | Not Started | 0% | Requirement Gathering | Medium
Development Phase | Mark Wilson | 2024-04-11 | 2024-06-30 | Not Started | 0% | Design Phase | High
Testing & QA | Sarah Lee | 2024-07-01 | 2024-07-31 | Not Started | 0% | Development Phase | High
User Training & Onboarding | David Park | 2024-08-01 | 2024-08-15 | Not Started | 0% | Testing & QA | Medium
Project Closure & Review | Jane Doe | 2024-08-16 | 2024-08-31 | Not Started | 0% | User Training & Onboarding | High
Total Tasks |  |  |  | 7