## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Dependencies | Priority
WP-001 | Define Workflow Objectives | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | None | High
WP-002 | Map Current Processes | John Doe | 2024-03-16 | 2024-04-01 | Not Started | WP-001 | Medium
WP-003 | Identify Bottlenecks | Lisa Chen | 2024-04-02 | 2024-04-15 | Not Started | WP-002 | High
WP-004 | Propose Process Improvements | Michael Brown | 2024-04-16 | 2024-05-01 | Not Started | WP-003 | High
WP-005 | Review and Approve Changes | Sarah Lee | 2024-05-02 | 2024-05-15 | Not Started | WP-004 | Critical