## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Priority | Resource Allocation | Milestones
WP-001 | Project Initiation & Planning | John Smith | 2024-03-15 | 2024-03-25 | 10 | In Progress | None | High | Project Manager, Business Analysts | Kick-off Meeting, Scope Finalization
WP-002 | Stakeholder Requirements Gathering | Sarah Johnson | <>2024-03-262024-04-10 | 15 | Pending Approval | WP-001 | Medium | Business Analysts, UX Team | Requirement Sign-off, User Interviews
WP-003 | Workflow Design & Process Mapping | Michael Brown | 2024-04-11 | 2024-04-30 | 20 | Not Started | WP-002 | High | Process Designers, IT Team | Draft Workflow Approved
WP-004 | Technology Stack Selection | Emily Davis | 2024-05-01 | 2024-05-15 | 15 | In Review | WP-003 | Critical | IT Engineers, DevOps Lead | Tech Evaluation Complete
WP-005 | Development & Prototype Building | Robert Lee | 2024-05-16 | 2024-06-30 | 45 | Not Started | WP-004 | High | Software Developers, QA Team | Prototype Demo, Code Review