## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (Days) | Budget (USD) | Status | Progress (%) | Resource Allocation
WP-001 | Workflow Process Mapping | Jane Doe | 2024-03-15 | 2024-03-25 | 10 | 15,000 | On Track | 85% | 2 Analysts, 1 Designer
WP-002 | Process Automation Design | John Smith | 2024-03-26 | 2024-04-10 | 15 | 30,000 | In Progress | 60% | 3 Engineers, 1 QA
WP-003 | Cost-Benefit Analysis of Automation | Lisa Chen | 2024-04-11 | 2024-04-18 | 7 | 8,500 | Planned | 0% | 1 Financial Analyst
WP-004 | Implementation Phase & Training | Mark Taylor | 2024-04-19 | 2024-05-31 | 43 | 75,000 | Not Started | 0% | 5 Team Members, 2 Trainers