## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies
Project Kickoff Meeting | Alex Rivera | 2024-03-01 | 2024-03-01 | Completed | 1 | -
Scope Definition & Stakeholder Alignment | Sam Chen | 2024-03-02 | 2024-03-07 | In Progress | 6 | Kickoff Meeting
Requirement Gathering Workshop | Jordan Lee | 2024-03-08 | 2024-03-14 | Not Started | 7 | Scope Definition
Design Phase & Prototyping | Mia Taylor | 2024-03-15 | 2024-03-28 | Not Started | 14 | Requirement Gathering
Development & Coding | Nate Kim | 2024-03-29 | 2024-04-15 | Not Started | 18 | Design Phase
Testing & Quality Assurance | Taylor Reed | 2024-04-16 | 2024-04-30 | Not Started | 15 | Development
User Acceptance Testing (UAT) | Lena Wong | 2024-05-01 | 2024-05-10 | Not Started | 10 | Testing & QA
Final Review & Deployment Plan | Alex Rivera | 2024-05-11 | 2024-05-15 | Not Started | 5 | UAT