## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Define Project Scope | Alice Johnson | 2024-03-15 | 2024-03-20 | In Progress | High
Identify Stakeholders | Bob Smith | 2024-03-18 | 2024-03-22 | Completed | Medium
Develop Workflow Diagrams | Carol Davis | 2024-03-21 | 2024-03-28 | Not Started | High
Conduct Stakeholder Review | Alice Johnson | 2024-03-29 | 2024-04-03 | Planned | Medium
Finalize Project Timeline | Bob Smith | 2024-04-05 | 2024-04-10 | Not Started | High