## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies | Priority | Resources Required
WP-001 | Project Initiation & Scope Finalization | Sarah Johnson | 2024-03-15 | 2024-03-25 | Completed | 10 | - | High | Project Manager, Legal Reviewer
WP-002 | Workflow Design & Process Mapping | Michael Chen | 2024-03-26 | 2024-04-10 | In Progress | 15 | WP-001 | High | Business Analyst, Process Designer
WP-003 | Stakeholder Alignment Workshop | Lena Torres | 2024-04-11 | 2024-04-15 | Planned | 5 | WP-002 | Medium | Facilitator, HR Representative
WP-004 | Technology Stack Selection | David Kim | 2024-04-16 | 2024-05-03 | Pending Approval | 18 | WP-002, WP-003 | High | IT Director, CTO
WP-005 | Development & Testing Phase | Team Alpha | 2024-05-04 | 2024-07-15 | Not Started | 73 | WP-004 | Critical | Full Dev Team, QA Engineers
WP-006 | Training & Change Management | Elena Martinez | 2024-07-16 | 2024-08-10 | Planned | 35 | WP-005 | Medium | Training Coordinator, Department Heads