## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Notes
Project Initiation | Alex Morgan | 2024-03-01 | 2024-03-15 | Completed | High |  | Finalize project scope and stakeholders.
Requirement Gathering | Samira Khan | 2024-03-16 | 2024-04-10 | In Progress | High | Project Initiation | Conduct interviews with key users and department heads.
Design Phase | Jordan Lee | 2024-04-11 | 2024-05-15 | Planned | Medium | Requirement Gathering | Develop wireframes and UI mockups.
Development Phase | Team Alpha | 2024-05-16 | 2024-07-31 | Not Started | High | Design Phase | Build core application features.
Testing & QA | Taylor Reed | 2024-08-01 | 2024-08-31 | Planned | High | Development Phase | Conduct unit, integration, and user acceptance testing.
Deployment | Marcus Chen | 2024-09-01 | 2024-09-05 | Not Started | High | Testing & QA | Deploy to production environment with rollback plan.
Post-Launch Review | All Team | 2024-09-06 | 2024-09-10 | Planned | Medium | Deployment | Collect feedback and document lessons learned.