## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Progress (%) | Notes
Define Project Scope | Jane Doe | 2024-04-01 | 2024-04-15 | Completed | - | 100% | Final scope approved by stakeholders.
Stakeholder Workshops | John Smith | 2024-04-16 | 2024-04-25 | In Progress | Scope Definition | 75% | Two sessions held; feedback collected.
Process Mapping & Analysis | Lisa Chen | 2024-04-26 | 2024-05-10 | Not Started | Workshop Results | 0% | Drafts to be reviewed by team lead.
Identify Process Gaps | Mark Taylor | 2024-05-11 | 2024-05-20 | Planned | Process Mapping | 0% | Gap analysis tools to be applied.
Propose Workflow Improvements | Sarah Kim | 2024-05-21 | 2024-06-05 | Not Started | Gap Analysis Results | 0% | Draft proposals under review.
Review & Approve Changes | Project Manager | 2024-06-06 | 2024-06-15 | Not Started | Improvement Proposals | 0% | Final approvals to be secured from leadership.