## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority
Project Initiation & Stakeholder Alignment | Jane Smith | 2024-03-15 | 2024-03-25 | Completed | None | High
Define Workflow Requirements | John Doe | 2024-03-26 | 2024-04-10 | In Progress | Initiation Phase | High
Workflow Design & Process Mapping | Lisa Chen | 2024-04-11 | 2024-04-30 | Not Started | Requirements Finalized | Medium
Stakeholder Review & Feedback Collection | Sarah Kim | 2024-05-01 | 2024-05-15 | Not Started | Design Complete | High
Implementation & System Integration | David Brown | 2024-05-16 | 2024-06-30 | Not Started | Feedback Finalized | High
Training & Change Management | Emma Wilson | 2024-07-01 | 2024-07-15 | Not Started | System Live | Medium
Post-Implementation Review & Optimization | Team Lead | 2024-07-16 | 2024-08-31 | Not Started | Training Complete | Low