## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority
Define Project Scope | Jane Doe | 2024-03-15 | 2024-03-20 | Completed | - | High
Conduct Stakeholder Analysis | John Smith | 2024-03-21 | 2024-03-25 | In Progress | Define Scope | Medium
Develop Workflow Design | Sarah Lee | 2024-03-26 | 2024-04-03 | Not Started | Stakeholder Analysis | High
Finalize Process Documentation | Michael Brown | 2024-04-04 | 2024-04-10 | Planned | Workflow Design | Medium
Training & Change Management | Emily Clark | 2024-04-11 | 2024-04-17 | Not Started | Documentation Finalized | High
Monitor & Optimize Workflow | David Kim | 2024-04-18 | 2024-05-01 | Not Started | Training Completed | Medium
Project Plan – Workflow Optimization ¦ One Page Template