## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Notes
Project Initiation | John Smith | 2024-03-01 | 2024-03-15 | Completed | - | Finalize project scope and stakeholders.
Requirements Gathering | Lisa Chen | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation | Conduct interviews with key departments.
Design Phase | Michael Lee | 2024-04-11 | 2024-05-05 | Planned | Requirements Gathering | Develop wireframes and UI mockups.
Development Phase | Sarah Kim | 2024-05-06 | 2024-07-15 | Not Started | Design Phase | Build core functionality using agile sprints.
Testing & QA | David Wang | 2024-07-16 | 2024-08-10 | Not Started | Development Phase | Perform unit, integration, and user acceptance testing.
Deployment | Emily Rodriguez | 2024-08-11 | 2024-08-15 | Not Started | Testing & QA | Launch application to production environment.
Post-Deployment Review | John Smith | 2024-08-16 | 2024-08-20 | Not Started | Deployment | Gather feedback and document lessons learned.