## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies | Priority
Project Kickoff Meeting | Jane Doe | 2024-04-01 | 2024-04-01 | 1 | Completed |  | High
Requirements Gathering | John Smith | 2024-04-02 | 2024-04-15 | 14 | In Progress | Kickoff Meeting | High
Workflow Design & Mockups | Alex Johnson | 2024-04-16 | 2024-05-05 | 21 | Not Started | Requirements Gathering | Medium
Development Phase | Team A | 2024-05-06 | 2024-06-15 | 40 | Not Started | Workflow Design & Mockups | High
Testing & Quality Assurance | Test Team | 2024-06-16 | 2024-07-05 | 21 | Not Started | Development Phase | High
User Training & Documentation | Maria Garcia | 2024-07-06 | 2024-07-15 | 10 | Not Started | Testing & QA | Medium
Go-Live & Post-Implementation Review | Project Manager | 2024-07-16 | 2024-07-18 | 3 | Not Started | User Training & Docs | High