## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority | Notes
Project Initiation & Scope Definition | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | - | High | Finalize project vision and stakeholder alignment.
Requirement Gathering & Analysis | Mark Johnson | 2024-03-16 | 2024-04-10 | In Progress | Initiation Phase | High | Conduct interviews with department heads.
Workflow Design & Process Mapping | Lisa Chen | 2024-04-11 | 2024-05-05 | Planned | Requirement Gathering | Medium | Develop visual process flows using BPMN.
Technical Feasibility Assessment | Alex Rodriguez | 2024-05-06 | 2024-05-20 | Not Started | Workflow Design | High | Evaluate tools and integration points.
Stakeholder Review & Approval | Sarah Kim | 2024-05-21 | 2024-06-03 | Planned | Technical Feasibility | High | Present draft workflow to leadership.
Implementation & Pilot Launch | Team Lead | 2024-06-04 | 2024-07-15 | Not Started | Stakeholder Approval | Critical | Deploy in selected departments with monitoring.