## Worksheet
Project Phase | Workflow Step | Responsible Team | Start Date | End Date | Status | Key Deliverable | Dependencies
Quarterly Planning | Workflow Audit | Operations & Strategy | 01/01/2024 | 03/31/2024 | In Progress | Audit Report & Process Map | Previous Q4 Review
Quarterly Planning | KPI Alignment | Analytics & Performance | 02/15/2024 | 04/30/2024 | Planned | KPI Dashboard v2.0 | Workflow Audit Complete
Execution Phase | Process Redesign | Engineering & Design | 04/01/2024 | 06/30/2024 | Pending Start | Revised Workflow Blueprint | KPI Alignment Finalized
Execution Phase | Automation Implementation | IT & DevOps | 05/10/2024 | 08/31/2024 | Not Started | Automated Workflow Engine | Process Redesign Approved
Review & Optimization | Performance Review | Leadership & Quality | 07/01/2024 | 09/30/2024 | Scheduled | Optimization Report & Action Plan | Automation Live & KPIs Collected