## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Resources Required
Project Initiation & Scoping | Sarah Johnson | 2024-03-01 | 2024-03-15 | In Progress | - | Project Manager, Stakeholder Meeting Room
Workflow Analysis & Mapping | Michael Chen | 2024-03-16 | 2024-04-05 | Not Started | Project Initiation & Scoping | Business Analyst, Process Documentation Tools
Process Redesign & Optimization | Emily Rodriguez | 2024-04-06 | 2024-05-10 | Not Started | Workflow Analysis & Mapping | UX Designers, Process Automation Tools
Pilot Implementation | David Kim | 2024-05-11 | 2024-06-15 | Not Started | Process Redesign & Optimization | IT Team, QA Team, 2 Internal Teams
Full-Scale Rollout | Sarah Johnson | 2024-06-16 | 2024-08-31 | Not Started | Pilot Implementation | All Departments, Training Modules, Support Team
Performance Evaluation & Feedback Loop | Michael Chen | 2024-09-01 | 2024-10-15 | Not Started | Full-Scale Rollout | HR Team, Process Review Panel, Analytics Tools
Workflow Optimization – Project Plan ¦ Report Version