## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days)
Project Initiation | John Doe | 2024-03-01 | 2024-03-07 | Completed | 7
Requirements Gathering | Jane Smith | 2024-03-08 | 2024-03-21 | In Progress | 14
Workflow Design | Alex Johnson | 2024-03-22 | 2024-04-05 | Not Started | 15
Development Phase | Team A | 2024-04-06 | 2024-05-15 | Not Started | 40
Testing & Validation | QA Team | 2024-05-16 | 2024-05-31 | Not Started | 16
Deployment & Review | Operations Lead | 2024-06-01 | 2024-06-15 | Not Started | 15