## Worksheet
Task | Owner | Start Date | End Date | Status | Notes
Define Project Goals | John Smith | 2024-03-01 | 2024-03-05 | Completed | Clarified vision and key objectives for the workflow improvement initiative.
Identify Key Processes | Emma Davis | 2024-03-06 | 2024-03-10 | In Progress | Mapping out current workflows from sales to invoicing.
Engage Stakeholders | Liam Chen | 2024-03-11 | 2024-03-15 | Pending | Schedule meetings with department heads to gather feedback.
Develop Workflow Blueprint | Sarah Kim | 2024-03-16 | 2024-03-25 | Not Started | Create visual diagrams and proposed process changes.
Pilot New Workflow | James Taylor | 2024-03-26 | 2024-04-05 | Not Started | Test the new process with a small team before full rollout.