## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies
Market Research & Analysis | Sarah Lin | 2024-03-15 | 2024-03-30 | In Progress | High | -
Product Vision Workshop | James Kim | 2024-04-01 | 2024-04-05 | Completed | High | Market Research & Analysis
MVP Feature Definition | Anna Patel | 2024-04-10 | 2024-04-25 | Planned | High | Product Vision Workshop
UI/UX Design Iteration | Luis Chen | 2024-05-01 | 2024-05-15 | In Progress | Medium | MVP Feature Definition
Technical Architecture Planning | David Ross | 2024-05-20 | 2024-06-05 | Pending | High | UI/UX Design Iteration
Development Sprint 1 | Engineering Team | 2024-06-10 | 2024-06-25 | Not Started | High | Technical Architecture Planning