## Worksheet
Task | Owner | Start Date | End Date | Status | Duration (Days) | Dependencies
Project Initiation | John Smith | 2024-03-01 | 2024-03-15 | Completed | 15
Requirements Gathering | Sarah Lee | 2024-03-16 | 2024-04-10 | In Progress | 35 | Project Initiation
Design Phase | Michael Chen | 2024-04-11 | 2024-05-15 | Planned | 45 | Requirements Gathering
Development | Team A (Dev) | 2024-05-16 | 2024-07-31 | Not Started | 77 | Design Phase
Testing & QA | Lisa Wong | 2024-08-01 | 2024-08-31 | Not Started | 31 | Development
Deployment & Go-Live | Alex Rodriguez | 2024-09-01 | 2024-09-15 | Planned | 15 | Testing & QA
Post-Implementation Review | Project Manager | 2024-09-16 | 2024-09-30 | Not Started | 15 | Deployment & Go-Live