## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority | Notes
Project Initiation & Scoping | Sarah Johnson | 2024-03-15 | 2024-03-25 | In Progress | - | High | Define goals, stakeholders, and success metrics.
Workflow Audit & Analysis | Mark Chen | 2024-03-26 | 2024-04-10 | Not Started | Project Initiation & Scoping | High | Identify bottlenecks and inefficiencies in current processes.
Process Redesign & Drafting | Lisa Ortiz | 2024-04-11 | 2024-05-05 | Not Started | Workflow Audit & Analysis | Medium | Develop new workflow diagrams and procedures.
Stakeholder Review & Feedback | Team Leadership Group | 2024-05-06 | 2024-05-15 | Not Started | Process Redesign & Drafting | High | Gather input from department heads and team leads.
Implementation & Training | James Rivera | 2024-05-16 | 2024-06-10 | Not Started | Stakeholder Review & Feedback | High | Roll out new workflow and conduct training sessions.
Post-Implementation Review | Sarah Johnson | 2024-06-11 | 2024-06-18 | Not Started | Implementation & Training | Medium | Evaluate effectiveness and document improvements.