## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Status | Dependencies
Project Initiation & Planning | John Smith | 2024-03-01 | 2024-03-15 | 15 | Completed
Requirements Gathering & Analysis | Jane Doe | 2024-03-16 | 2024-04-10 | 35 | In Progress | Project Initiation & Planning
Design Phase (UI/UX) | Mike Chen | 2024-04-11 | 2024-05-05 | 35 | Not Started | Requirements Gathering & Analysis
Development Phase (Frontend) | Sarah Lee | 2024-05-06 | 2024-06-15 | 40 | Not Started | Design Phase (UI/UX)
Development Phase (Backend) | David Kim | 2024-05-16 | 2024-07-10 | 65 | Not Started | Design Phase (UI/UX)
Testing & Quality Assurance | Linda Brown | 2024-07-11 | 2024-08-15 | 45 | Not Started | Development Phase (Frontend), Development Phase (Backend)
Deployment & Go-Live | Tom White | 2024-08-16 | 2024-08-16 | 1 | Not Started | Testing & Quality Assurance
Post-Deployment Review & Feedback Loop | All Team Members | 2024-08-17 | 2024-08-31 | 15 | Not Started | Deployment & Go-Live