## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | Duration (days) | Dependencies | Priority | Progress (%)
WP-001 | Project Initiation & Stakeholder Alignment | John Smith | 2024-03-15 | 2024-03-25 | Completed | 10 |  | High | 100%
WP-002 | Scope Definition & Requirement Gathering | Sarah Lee | 2024-03-26 | 2024-04-10 | In Progress | 15 | WP-001 | High | 75%
WP-003 | Work Breakdown Structure (WBS) Finalization | Michael Chen | 2024-04-11 | 2024-04-18 | Planned | 7 | WP-002 | Medium | 0%
WP-004 | Resource Allocation & Team Assignment | Emma Brown | 2024-04-19 | 2024-04-25 | Pending Approval | 6 | WP-003 | High | 0%
WP-005 | Design & Prototyping Phase | Liam Taylor | 2024-04-26 | 2024-05-15 | Not Started | 20 | WP-004 | Medium | 0%