## Worksheet
Week | Project Phase | Key Activities | Responsible Team | Deadline | Status | Priority th>
Week 1 | Initiation | Define project scope, stakeholders, objectives | Project Steering Committee | 2024-04-07 | On Track | High
Week 2 | Requirements Gathering | Conduct interviews, document user needs | Product & UX Team | 2024-04-14 | In Progress | High
Week 3 | Design & Prototyping | Create wireframes, high-fidelity mockups | Design Team | 2024-04-21 | Planned | Medium
Week 4 | Development Sprint | Develop core features, integrate APIs | Engineering Team | 2024-04-28 | Not Started | High
Week 5 | Testing & QA | Conduct unit, integration, and user testing | QA & DevOps Team | 2024-05-05 | Not Started | High
Week 6 | Deployment & Review | Deploy to staging, conduct review meetings | Operations & Project Lead | 2024-05-12 | Not Started | High