## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies | Notes
Project Kickoff Meeting | Project Manager | 2024-04-01 | Completed | High | None | Finalize project scope and objectives.
Workflow Requirements Gathering | Business Analyst | 2024-04-10 | In Progress | Medium | Project Kickoff Meeting | Interview stakeholders to define current workflow bottlenecks.
Process Mapping & Analysis | Process Designer | 2024-04-18 | Planned | High | Requirements Gathering | Create visual flowcharts to identify inefficiencies.
Optimization Strategy Development | Project Lead | 2024-05-05 | Not Started | High | Process Mapping & Analysis | Propose automation and reallocation strategies.
Stakeholder Review & Feedback | Project Manager | 2024-05-15 | Scheduled | Medium | Strategy Development | Gather input from department heads on proposed changes.
Implementation & Training | Operations Team | 2024-06-01 | Not Started | High | Stakeholder Review & Feedback | Roll out optimized workflow with team training sessions.