## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Key Deliverables | Status | Risk Level
Requirement Gathering | Project Manager & Stakeholders | 7 | Detailed workflow specifications, stakeholder feedback report | On Track | Low
Process Design & Mapping | Process Analysts | 10 | Flowchart, process map, compliance checklist | On Track | Medium
Technology Integration Plan | IT Team & DevOps | 14 | System compatibility report, API integration plan | On Track | High
Pilot Testing Phase | Quality Assurance Team | 12 | Test results, bug logs, performance metrics | Delayed (by 2 days) | Medium
Full Deployment | Operations & Project Manager | 5 | Go-live report, user training summary | Pending Approval | Low