## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Remarks
Project Initiation | Project Manager | 05/01/2024 | Completed | Approved budget and scope document.
Stakeholder Alignment | Business Analyst | 05/15/2024 | In Progress | Finalizing requirements workshop notes.
Process Mapping | Operations Lead | 06/05/2024 | Pending | Draft flowcharts shared with team for review.
Risk Assessment | Risk Officer | 06/20/2024 | Not Started | Identifying potential bottlenecks and dependencies.
Workflow Implementation Plan | Project Manager & IT Team | 07/10/2024 | Not Started | To be developed based on process mapping feedback.
Training & Change Management | HR & Training Lead | 08/05/2024 | Not Started | Developing training materials and schedule.
Performance Review & Optimization | Project Manager & QA Team | 09/30/2024 | Not Started | Evaluate KPIs and refine workflow based on feedback.