## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes
Project Initiation | Project Manager | 2024-03-15 | Completed | Initial scope and objectives approved.
Stakeholder Alignment | Client Liaison Officer | 2024-03-22 | In Progress | Finalizing requirements with key stakeholders.
Work Plan Development | Operations Team | 2024-04-05 | Pending | Current draft under review.
Risk Assessment & Mitigation | Risk Management Specialist | 2024-04-10 | Not Started | Identifying potential risks and controls.
Resource Allocation | HR & Finance Department | 2024-04-15 | Planned | Budget and staffing finalized.