## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Project Kickoff Meeting | Jane Doe | 2024-04-01 | Completed | High | Confirmed agenda and stakeholders.
Requirement Gathering | John Smith | 2024-04-08 | In Progress | High | Interviews with key users scheduled.
Workflow Design Draft | Lisa Chen | 2024-04-15 | Not Started | Medium | Initial flowchart to be reviewed.
Stakeholder Review Session | Team Lead | 2024-04-22 | Planned | High | Feedback collection and adjustments.
Final Approval & Launch | Director | 2024-04-30 | Not Started | Critical | Approval required before go-live.