## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Project Kickoff Meeting | John Smith | 2024-03-15 | Completed | High | All team members briefed on goals and timelines.
Requirements Gathering | Sarah Johnson | 2024-03-25 | In Progress | High | Stakeholder interviews scheduled and recorded.
Design Phase Review | Mike Brown | 2024-04-10 | Pending | Moderate | Design mockups approved by UX team.
Development Start | Lisa Chen | 2024-04-15 | Not Started | High | Code repository initialized. Sprint planning in progress.
Testing & QA | David Lee | 2024-05-10 | Not Started | Moderate | Test cases drafted. Environment ready upon request.
Deployment to Production | Emma Taylor | 2024-05-20 | Not Started | High | Final review and rollback plan in place.