## Worksheet
Workflow Stage | Responsibility | Key Activities | Timeline (Days) | Budget Allocation ($) | KPIs & Metrics | Risk Assessment
Initiation | Project Sponsor & Steering Committee | Define objectives, scope, and success criteria | 5 | $15,000 | Scope clarity, stakeholder alignment (≥90%) | Stakeholder misalignment risk
Requirements Gathering | Business Analysts & Department Heads | Conduct workshops, document needs, validate requirements | 10 | $30,000 | Requirement completeness (≥95%), accuracy rate | Incomplete data collection risk
Design & Planning | UX Designers, Process Engineers | Create workflow diagrams, process maps, system designs | 12 | $45,000 | Design usability score (≥8.5/10), compliance check | Design deviation from scope risk
Development & Implementation | IT Team, Developers, QA Engineers | Build system modules, integrate processes, conduct testing | 30 | $120,000 | Defect rate (<5%), deployment success rate (≥99%) | Technical failure, integration delay
Training & Change Management | HR Team, Change Managers | Conduct training sessions, deploy communication plans | 7 | $20,000 | User adoption rate (≥85%), feedback score (≥4.2/5) | Resistance to change, poor engagement
Monitoring & Optimization | Operations Team, Analytics Group | Track KPIs, conduct monthly reviews, refine workflows | Ongoing | $25,000/year | Cycle time reduction (≥10%), cost savings (%) | Data availability delays, process drift