## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-03-15 | Completed | High | Finalize scope and objectives with stakeholders.
Requirement Gathering | Michael Chen | 2024-03-25 | In Progress | High | Conduct interviews with key users and departments.
Design Mockups | Lisa Rodriguez | 2024-04-10 | Planned | Medium | Create wireframes and UI designs for all screens.
Development Phase | David Kim | 2024-05-15 | Not Started | High | Begin backend and frontend implementation.
Testing & QA | Emma Thompson | 2024-06-05 | Not Started | High | Execute unit, integration, and user acceptance tests.
Deployment | Alex Brown | 2024-06-15 | Not Started | High | Deploy to production environment with monitoring.
Post-Launch Review | Team Lead | 2024-06-30 | Not Started | Medium | Gather feedback and document lessons learned.