## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources Required | Dependencies
Initiate Project Kickoff Meeting | Project Manager | 01/05/2024 | 01/06/2024 | Completed | High | Project Manager, Stakeholders | None
Define Project Scope and Objectives | Business Analyst | 01/07/2024 | 01/15/2024 | High | Medium | Business Analyst, Department Heads | Kickoff Meeting Results
Develop Workflow Process Map | Process Engineer | 01/16/2024 | 01/25/2024 | Medium | High | Process Engineer, Operations Team | Scope Document Approval
Conduct Stakeholder Workshops | Project Coordinator | 01/28/2024 | 02/01/2024 | Medium | Medium | Project Coordinator, Department Representatives | Process Map Draft Available
Refine Workflow with Feedback | Process Engineer | 02/04/2024 | 02/10/2024 | Medium | Medium | Process Engineer, Quality Assurance | Workshop Feedback Summary
Finalize and Approve Workflow Document | Project Manager | 02/11/2024 | 02/14/2024 | High | High | Project Manager, CTO, CFO | All Feedback Integrated