## Worksheet
Workflow Step | Responsible Role | Deadline | Status | Remarks
Project Initiation | Project Manager | 01/15/2024 | Completed | Approved budget and scope defined.
Stakeholder Alignment | Project Manager & PMO | 01/25/2024 | In Progress | Finalizing requirements with key clients.
Risk Assessment | Risk Analyst | 02/05/2024 | Pending | Initial risk matrix prepared.
Resource Planning | HR & Operations Lead | 02/10/2024 | Not Started | Team availability confirmed.
Workflow Design | Process Engineer | 03/01/2024 | Blocked | Dependency on third-party tool approval.