## Worksheet
Workflow Optimization - Project Template (Monthly)
Week | Objective | Key Activities | Responsible Party | Status | Notes/Comments
Week 1 | Assess current workflow efficiency | Process mapping, stakeholder interviews, data collection | Project Manager & Operations Lead | Pending | No action yet; initial planning in progress.
Week 2 | Identify bottlenecks and inefficiencies | Analyze process data, create flow diagrams, flag delays | Process Analyst & Team Lead | In Progress | Bottlenecks identified in approval stages.
Week 3 | Propose optimized workflow solutions | Develop alternative workflows, conduct mock-ups | Design Team & Project Manager | Planned | Preliminary solutions reviewed internally.
Week 4 | Stakeholder review & feedback collection | Presentation to stakeholders, gather input, refine options | Stakeholder Coordinator & Project Manager | Scheduled | Review date set for Thursday, 15th.
Week 5 | Finalize and implement new workflow | Train staff, roll out changes, monitor launch | Operations Team & IT Support | Pending Approval | Requires sign-off from Executive Team.
Week 6 | Evaluate impact & measure KPIs | Track cycle time, error rate, throughput metrics | Project Manager & Analytics Lead | To Be Conducted | Monthly review scheduled for 30th.