## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes
Project Initiation | Project Manager | 01/15/2024 | Completed | Approved budget and scope documented.
Stakeholder Alignment | Team Lead | 01/22/2024 | In Progress | Meeting scheduled for 15 mins with key stakeholders.
Requirement Gathering | Business Analyst | 02/05/2024 | Pending | Feedback from users to be collected and reviewed.
Design & Prototyping | UI/UX Designer | 02/19/2024 | Not Started | Wireframes and user flows to be developed.
Development Phase | Development Team | 03/15/2024 | Not Started | MVP features to be coded and tested.
Quality Assurance | QA Manager | 04/01/2024 | Not Started | Testing scenarios and bug tracking setup.
Deployment Plan | IT Operations | 04/10/2024 | Pending | Environment setup and rollback procedures defined.
Post-Launch Review | Project Manager | 04/20/2024 | Not Started | Gather feedback and evaluate KPIs.