## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies
Define Project Scope | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | High | None
Stakeholder Alignment Meeting | John Doe | 2024-03-16 | 2024-03-17 | Planned | Medium | Define Project Scope
Requirements Gathering | Alex Chen | 2024-03-18 | 2024-04-05 | In Progress | High | Stakeholder Alignment Meeting
Design Phase Planning | Sam Patel | 2024-04-06 | 2024-04-15 | Not Started | Medium | Requirements Gathering
Development Kickoff | Lisa Wong | 2024-04-16 | 2024-05-31 | Planned | High | Design Phase Planning