## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Notes / Remarks
Project Initiation & Scope Definition | Project Manager | 2024-03-15 | Pending | Finalize scope with stakeholders.
Stakeholder Requirements Gathering | Business Analyst | 2024-03-22 | In Progress | Conduct workshops with key departments.
Workflow Design & Process Mapping | Process Engineer | 2024-04-05 | Not Started | Create visual process flow diagrams.
Resource Allocation & Team Assignment | Project Manager | 2024-04-10 | Pending | Finalize team structure and roles.
Approval & Sign-off from Leadership | Project Sponsor | 2024-04-15 | Not Started | All documentation must be ready.
Implementation & Pilot Run | IT Team & Operations | 2024-05-01 | Not Started | Pilot in selected department.
Performance Review & Feedback Loop | Project Manager & Stakeholders | 2024-05-15 | Not Started | Gather input for optimization.