## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies
Project Kickoff Meeting | Jane Doe | 2024-03-15 | Completed | Low
Requirements Gathering | John Smith | 2024-03-25 | In Progress | Medium | Kickoff Meeting
Design Finalization | Lisa Chen | 2024-04-10 | Pending | High | Requirements Gathering
Development Phase Start | Mike Johnson | 2024-04-20 | Not Started | High | Design Finalization
Testing & QA Review | Sarah Lee | 2024-05-15 | Not Started | Medium | Development Phase Start
Project Review & Delivery | Team Lead | 2024-05-30 | Not Started | High | Testing & QA Review