## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Progress (%)
Project Initiation | Alice Johnson | 2024-03-01 | 2024-03-15 | Completed | Low |  | 100
Requirement Gathering | Bob Smith | 2024-03-16 | 2024-04-10 | In Progress | Medium | Project Initiation | 75
Design Phase | Carol Lee | 2024-04-11 | 2024-05-05 | Not Started | High | Requirement Gathering | 0
Development Phase | David Brown | 2024-05-06 | 2024-07-15 | Not Started | High | Design Phase | 0
Testing & QA | Eva Martinez | 2024-07-16 | 2024-08-10 | Not Started | High | Development Phase | 0
Deployment | Frank Wilson | 2024-08-11 | 2024-08-15 | Not Started | Medium | Testing & QA | 0