## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority | Progress (%)
Project Initiation & Stakeholder Alignment | Sarah Johnson | 2024-03-01 | 2024-03-15 | Completed | - | High | 100%
Requirements Gathering & Analysis | David Kim | 2024-03-16 | 2024-04-10 | In Progress | Initiation Phase | High | 65%
Workflow Design & Process Mapping | Lisa Chen | 2024-04-11 | 2024-05-05 | Not Started | Requirements Gathering | Medium | 0%
Technology Selection & Tool Integration | Michael Reed | 2024-05-06 | 2024-06-15 | Planned | Workflow Design | High | 0%
Pilot Implementation & Feedback Loop | Emily Torres | 2024-06-16 | 2024-07-31 | Not Started | Technology Selection | High | 0%
Full-Scale Deployment & Training | James Wilson | 2024-08-01 | 2024-09-30 | Not Started | Pilot Implementation | Critical | 0%
Post-Implementation Review & Optimization | All Team Leads | 2024-10-01 | 2024-10-31 | Not Started | Full-Scale Deployment | Medium | 0%