## Worksheet
Task | Start Date | End Date | Responsible Party | Status | Dependencies | Notes
Project Initiation & Stakeholder Alignment | 2024-03-01 | 2024-03-15 | Project Manager | Completed | - | Finalize scope and key stakeholders.
Requirement Gathering & Analysis | 2024-03-16 | 2024-04-10 | Business Analysts | In Progress | Initiation & Alignment | Interviews with end users and departments.
Work Breakdown Structure (WBS) Development | 2024-04-11 | 2024-04-25 | Project Manager & Team | Planned | Requirement Gathering | Break down project into manageable phases.
Design & Prototyping Phase | 2024-04-26 | 2024-05-31 | UX/UI Designers | Not Started | WBS Development | Create wireframes and user flows.
Development & Coding Phase | 2024-06-01 | 2024-08-15 | Software Developers | Planned | Design & Prototyping | Build core application features.
Testing & Quality Assurance | 2024-08-16 | 2024-09-10 | QA Engineers | Not Started | Development Phase | Conduct unit, integration, and user acceptance tests.
Deployment & Go-Live | 2024-09-11 | 2024-09-15 | DevOps Team | Planned | Testing & QA | Deploy to production environment.
Post-Implementation Review & Optimization | 2024-09-16 | 2024-10-31 | Project Manager & Analysts | Not Started | Deployment & Go-Live | Collect feedback, measure KPIs, and refine workflows.