## Worksheet
Month | Phase | Key Activities | Responsible Team | Milestone Due Date | Status
January | Initiation & Planning | Project kickoff, stakeholder alignment, scope definition | Project Office & Strategy Team | 01/31/2024 | Completed
February | Requirements Gathering | Workshop sessions, requirement documentation, validation | Product & UX Team | 02/28/2024 | In Progress
March | Design & Prototyping | Wireframe development, user testing, design refinement | Design & UX Team | 03/31/2024 | Planned
April | Development & Build | Frontend and backend development, API integration | Engineering Team | 04/30/2024 | <Scheduled
May | Testing & Quality Assurance | Functional, performance, and security testing | QA & DevOps Team | 05/31/2024 | Planned
June | Deployment & Go-Live | Staging deployment, user training, go-live execution | Operations & Support Team | 06/30/2024 | Scheduled
July | Post-Implementation Review | Performance analysis, feedback collection, optimization plan | Project Office & Analytics Team | 07/31/2024 | Planned
August | Continuous Improvement Cycle | Workflow adjustments, KPI monitoring, process documentation | All Teams | 08/31/2024 | Ongoing
September | Annual Review & Planning | Year-end evaluation, next year roadmap planning | Project Office & Leadership Team | 09/30/2024 | Scheduled
October | Optimization & Scaling | Process scaling, automation initiatives, resource reallocation | Operations & Innovation Team | 10/31/2024 | Planned
November | Stakeholder Reporting & Feedback | Monthly performance reports, user feedback sessions | Project Office & Communications Team | 11/30/2024 | Scheduled
December | Year-End Closure & Planning Review | Final evaluation, lessons learned, budget review | Project Office & Finance Team | 12/31/2024 | Completed