## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority
Project Initiation | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | - | High
Requirement Gathering | John Smith | 2024-03-16 | 2024-04-10 | In Progress | Project Initiation | High
Design Phase | Lisa Chen | 2024-04-11 | 2024-05-05 | Planned | Requirement Gathering | Medium
Development | Mark Taylor | 2024-05-06 | 2024-07-15 | Not Started | Design Phase | High
Testing & QA | Sarah Kim | 2024-07-16 | 2024-08-10 | Pending Approval | Development | High
Deployment | David Lee | 2024-08-11 | 2024-08-15 | In Progress | Testing & QA | Medium
Post-Implementation Review | Jane Doe | 2024-08-16 | 2024-08-25 | Scheduled | Deployment | Low