## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Initiation | 01/01/2024 | 01/15/2024 | Project Manager | Completed
Requirements Gathering | 01/16/2024 | 02/14/2024 | Business Analysts | In Progress
Design Phase | 02/15/2024 | 03/15/2024 | UX & UI Team | Planned
Development Phase | 03/16/2024 | 05/31/2024 | Software Developers | Not Started
Testing & Quality Assurance | 06/01/2024 | 07/15/2024 | QA Team | Not Started
Deployment & Launch | 07/16/2024 | 07/31/2024 | Operations Team | Not Started
Post-Launch Review | 08/01/2024 | 08/15/2024 | Project Manager | Not Started