## Worksheet
Date | Task | Owner | Status | Duration (hrs) | Dependencies | Notes
2023-10-03 | Project Kickoff Meeting | Jane Smith | Completed | 4 | - | Confirmed all stakeholders and objectives.
2023-10-04 | Requirement Gathering | John Doe | In Progress | 6 | Kickoff Meeting | Collecting inputs from business units.
2023-10-05 | Workflow Design Draft | Alice Johnson | Not Started | 8 | Requirement Gathering | Initial flow diagrams being created.
2023-10-06 | Stakeholder Review | Team Lead | Scheduled | 3 | Workflow Design Draft | Finalize design with key stakeholders.
2023-10-07 | Approval & Sign-off | Director | Not Started | 2 | Stakeholder Review | All documentation to be reviewed and signed.