## Worksheet
Phase | Activity | Start Date | End Date | Responsible Team | Status | Dependencies
Initiation | Define Project Scope & Objectives | 2024-03-15 | 2024-03-20 | Project Steering Committee | Completed | -
Planning | Develop Workflow Process Map | 2024-03-21 | 2024-04-05 | Process Optimization Team | In Progress | Initiation Phase Completion
Execution | Pilot Workflow Implementation | 2024-04-06 | 2024-05-10 | Operations & IT Team | Pending | Planning Phase Completion
Review & Adjustment | Analyze Performance Metrics & Refine Process | 2024-05-11 | 2024-06-05 | Data Analytics Team | Not Started | Execution Phase Completion
Deployment | Full-Scale Workflow Rollout | 2024-06-06 | 2024-07-15 | All Departments | Not Started | Review & Adjustment Phase Completion